## Item 10
Anticipated Development Delivery |  |  |  | July 2014
Phase | Period | Housing Delivery | Description | Ptarmigan Planning / Leach Homes Role
1 | 2016-2021 | 400 | Outline planning consent for development will be secured in 2017 with detailed planning secured over 2018. Development will commence on site in 2019 with first occupations being achieved in 2020. 200 houses will be delivered in 2020 and 2021 with 2-3 house-builders being on site at any one time. | As a land promoter Ptarmigan Planning would sell the site with their landowners once outline planning has been achieved. Land would be sold in tranches and would typically follow the order of the development's phasing strategy. As a house-builder Leach Homes would build out the housing on the land they control. A proportion of their land would also potentially be sold to other house-builders.
2 | 2021 - 2026 | 1000 | 200 houses will be delivered per year with between 3-4 house-builders being on site at any one time. | As a land promoter Ptarmigan Planning would sell the site with their landowners once outline planning has been achieved. Land would be sold in tranches and would typically follow the order of the development's phasing strategy. As a house-builder Leach Homes would build out the housing on the land they control. A proportion of their land would also potentially be sold to other house-builders.
3 | 2026-2031 | 1000 | 200 houses will be delivered per year with between 3-4 house-builders being on site at any one time. | As a land promoter Ptarmigan Planning would sell the site with their landowners once outline planning has been achieved. Land would be sold in tranches and would typically follow the order of the development's phasing strategy. As a house-builder Leach Homes would build out the housing on the land they control. A proportion of their land would also potentially be sold to other house-builders.
4 | 2031 - 2036 | 572 | 200 houses will be delivered per year with between 2-3 house-builders being on site at any one time. | Ptarmigan Planning unlikely to be involved, with all of the land they control having been purchased by house-builders. Leach Homes will remain on site and continue to deliver housing as well as potentially selling some of the land to other house-builders.